## Slide 1: Checklist #2
Kenzie Fowler, Christine Wu, William Chen, and Taylor Moss

## Slide 2: Project Management Approach
Waterfall method
XYZ Inc has an estimated completion date of March 2022
  Deadlines must be set in place to ensure we reach this deadline
Known deadlines, budget, and expected outcomes
We will be onsite for the majority of the project
Everything will be documented, so if one of us is unavailable, the project will continue as planned

## Slide 3: Engagement Type
Combination of strategic planning and current state analysis
Current state analysis - establish a baseline to compare to other organizations
  Identify new business opportunities for XYZ’s expansion
  Examine the work culture to achieve XYZ’s goals
  Identify policies that need change/revision
Strategic planning - set priorities and establish mutual goals between employees
  Set operation priorities to maximize employee performance
  Adjust XYZ’s direction to allow them to expand their company
  Measure employee satisfaction for retention rates

## Slide 4: Timeline
Present findings and solutions
Propose solutions and conduct a meeting for approval
Discuss implementation plans
Debrief
March
Finalize solutions
Compile and compare XYZ hiring advantages and disadvantages to other organizations. Conduct meetings
Finalize the solutions and create an implementation plan (separate timeline)
February
Gather incentives
Study market incentive programs and compile a list of possible solutions
Create a plan for marketing and potential equity offers
Find professionals that can provide insight into marketing
January
Study tech market
Analyze the tech market for potential opportunities for XYZ expansion
Present the top three opportunities and receive feedback
Based on feedback, study ways to enter the new market to meet regulations and requirements
December
Start project
Conduct multiple meetings with randomly selected employees
Conduct surveys on Twitter and Facebook to gather feedback
Study other organizations and compile hiring advantages compared to XYZ. Conduct meetings
November
Meet with XYZ to discuss project plans
Establish goals, needs, and wants for the outcome.
Complete current state analysis
October

## Slide 5: Deliverables
Survey results from social media
Survey results from employees
Comparison list of hiring advantages and disadvantages between XYZ and other organizations
List of possible solutions
Top three markets XYZ can enter with a list of pros and cons for each

## Slide 6: Major workstreams, Tasks, and Steps
Christine Wu: Analyze IT market and ways to improve XYZ job marketing. Find ways to incentivize future employees and analyze larger organizations
William Chen: Conduct current state analysis and research IT market for potential expansions. Conduct meetings with employees and outsiders to receive feedback on XYZ Inc, expansions, and solutions
Taylor Moss: Plan the project and create deadlines for us (the consultants). Conduct and lead research and meetings with XYZ
Kenzie Fowler: Conduct market research and develop ways for XYZ to promote itself. Lead in advertising

## Slide 7: Major workstreams, Tasks, and Steps (Continued)
Everyone will assist each other throughout the project (even if the timeline says they don’t start yet)
William - Begin current state analysis from mid-October to March
  Observe work culture, interview employees, identify strengths and weaknesses, and conduct group meetings
Christine - Conduct research in IT markets from December to March
  Research demanding fields and regulations/requirements to enter the market. Use feedback from employee surveys to compile a list of wants. Study larger cloud service companies
Kenzie - Conduct market research from November to March
  Analyze XYZ’s current hiring strategies and develop improvement plans for the company.
Taylor - Create deadlines and manage the project from October to March
  Create deadlines and set milestones based on XYZ’s budget and estimated completion date. Conduct group meetings with executives to discuss progress and expectations.

## Slide 8: Discovery Phase and What Will Come From it
Discovery is the main objective (the majority of the research and solutions will come from this phase)
The discovery phase allows us to analyze the tech market to find any gaps or ideas for the problem our company is facing
The discovery phase helps us make decisions based on data and removes the risks of scope creep, going over budget, and missing deadlines
The objective of the discovery phase is to analyze and identify the goals and solutions for XYZ’s problem
  We will have a meeting to present and agree on our recommended solution
Our analysis of how we can solve the problem using the data will be our final recommendation
We plan on including a recommendation on how to go about implementing our solution
  The implementation plan will be derived from the insights that we gathered to solve the problem in the most feasible way

## Slide 9: Types of data points needed
Qualitative Research
  Surveys/interviews from impacted tech businesses in these shortages of staff
  Surveys/Interviews of employees on what makes a company attract them (or what compels them to stay at XYZ)
Quantitative Research
  Number of current employees in the tech field
  Number of needed tech employees in every field
  Number of people looking for jobs in the tech field
Market Research
  Statistics found from various sources that show what is going on in the hiring industry (and tech industry) and why it is a real problem
  How companies have developed ways to incentivize employees to join their organization
  What the impacts will be on the smaller tech companies

## Slide 10: Next Steps
  By March, we will have proposed our solutions based on our discoveries.
    Meet with board members
    Solve how to expand XYZ’s business and make it attract top talent
  Our final recommendations will be how to go about implementing this solution.
    Implementation is a separate project that follows this one (after the client approves solutions)