## RACI Template
Project task or deliverable | Kenzie Fowler (Advertiser & Client Relations) | Christine Wu (Market Analyst/Researcher) | William Chen (Business Analyst) | Taylor Moss (Project Manager/Strategic Planner) | Project Sponsor | Executive Sponsor | XYZ Employees
Social media survey (deliverable) | R | R | C/I | A | C/I | C/I
Employee survey (deliverable) | I | C/I | R | A | C/I | C/I
Hiring advantages/disadvantages comparison (deliverable) | R | R | R | A | C/I | C/I
Create recommendations | C | C | C | R/A | I | I
Top 3 markets for XYZ (deliverable) | C/I | R | C/I | A | C/I | C/I
Analyze IT market/corporations | I | R | C | R/A |  |  | C
Current state analysis | I | C | R | R/A | I | I | C
Market Research | R | R | C | R/A | I |  | C
Finalize Solution | C/I | C/I | C/I | C/I | A | R
Solution Implementation & Training | C/I | C/I | C/I | R | A | I | I

## RACI Example
RACI CHART TEMPLATE |  | Build better gantt charts with TeamGantt for FREE!
Project task or deliverable | Project manager | Strategist | Designer | Front-end developer | Back-end developer
Design sitemap | C | R | A | I | I
Design wireframes | C | A | R | I | I
Create style guide | A | C | R | C | I
Code templates | A | I | C | R | C

## RACI Definitions
Responsible | This team member does the work to complete the task. Every task needs at least one Responsible party, but it’s okay to assign more.
Accountable | This person delegates work and is the last one to review the task or deliverable before it’s deemed complete. On some tasks, the Responsible party may also serve as the Accountable one. Just be sure you only have one Accountable person assigned to each task or deliverable. (Note: It might not be your PM!)
Consulted | Every deliverable is strengthened by review and consultation from more than one team member. Consulted parties are typically the people who provide input based on either how it will impact their future project work or their domain of expertise on the deliverable itself.
Informed | These team members simply need to be kept in the loop on project progress, rather than roped into the details of every deliverable.

## RACI assignment drop-down data
R | This worksheet is purely admnistrative. The letters in column A feed the formula that auto-populates the RACI assignment drop-down on other tabs. Making changes here could impact the formula on your RACI Template and RACI Example worksheets.
A
C
I